## Project Schedule
[6 empty] | Project start: | [7 empty] | 2025-05-28
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-05-26 to 2025-07-20
 | time axis 2025-05-26 to 2025-07-20
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Ideation
| Define Problem Statement | All Team |  | 2025-05-28 | 2025-05-29
| UI Wireframing | Janhavi Pawar and Tejaswini Kolapkar |  | 2025-05-29 | 2025-06-02
| ERD chart and Mind Maps | Shravani Pidurkar |  | 2025-05-29 | 2025-06-02
| Gantt Chart | Janhavi Pawar |  | 2025-05-29 | 2025-06-02
| RACI Chart | Tejaswini Kolapkar |  | 2025-05-29 | 2025-06-02
| Project Charter | Tanvi Tonge |  | 2025-05-29 | 2025-06-02
Design and Prototyping
| Create detailed wireframe | Janhavi Pawar |  | 2025-06-02 | 2025-06-04
| Finalize databara ERD | Shravani Pidurkar |  | 2025-06-02 | 2025-06-04
| Finalize UI/UX designer | Tejaswini Kolapkar |  | 2025-06-02 | 2025-06-04
| Create APl-endpoint plan | Tanvi Tonge |  | 2025-06-02 | 2025-06-05
Implementation
| Database Creation & Management | Tanvi Tonge |  | 2025-06-06 | 2025-06-12
| Frontend Development | Janhavi Pawar and Shravani Pidurkar |  | 2025-06-08 | 2025-06-14
| Backend API development | Janhavi Pawar, Shravani Pidurkar and Tanvi Tonge |  | 2025-06-08 | 2025-06-14
| Integration and Testing | Tejaswini Kolapkar and Janhavi Pawar |  | 2025-06-13 | 2025-06-15
Testing, Deployment and Review
| Testing & Bug Fixing | Janhavi Pawar |  | 2025-06-15 | 2025-06-17
| Final Deployment | Tanvi Tonge |  | 2025-06-17 | 2025-06-18
| Final demo and Presentation | Tejaswini Kolapkar |  | 2025-06-18 | 2025-06-19
| Project Documentation | Shravani Pidurkar |  | 2025-06-19 | 2025-06-20

## Project actual
[7 empty] | Project Start Date | [7 empty] | 2025-05-28
[7 empty] | Current Week | [7 empty] | 2
[7 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-06-02 to 2025-07-27
 | time axis 2025-06-02 to 2025-07-27
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Ideation
| Define Problem Statement | All Team | 100% | 2025-05-28 | 2025-05-29 | 2
| UI Wireframing | Janhavi Pawar and Tejaswini Kolapkar | 100% | 2025-05-29 | 2025-06-02 | 5
| ERD chart and Mind Maps | Shravani Pidurkar | 100% | 2025-05-29 | 2025-06-02 | 5
| Gantt Chart | Janhavi Pawar | 100% | 2025-05-29 | 2025-06-02 | 5
| RACI Chart | Tejaswini Kolapkar | 100% | 2025-05-29 | 2025-06-02
| Project Charter | Tanvi Tonge | 100% | 2025-05-29 | 2025-06-02 | 5
Design and Prototyping
| Create detailed wireframe | Janhavi Pawar | 100% | 2025-06-02 | 2025-06-04 | 3
| Finalize databara ERD | Shravani Pidurkar | 100% | 2025-06-02 | 2025-06-04 | 3
| Finalize UI/UX designer | Tejaswini Kolapkar | 100% | 2025-06-02 | 2025-06-04 | 3
| Create APl-endpoint plan | Tanvi Tonge | 100% | 2025-06-02 | 2025-06-05 | 4
Implementation
| Database Creation & Management | Tanvi Tonge | 80% | 2025-06-06 | 2025-06-12 | 7
| Frontend Development | Janhavi Pawar and Shravani Pidurkar | 35% | 2025-06-08 | 2025-06-14
| Backend API development | Janhavi Pawar, Shravani Pidurkar and Tanvi Tonge | 35% | 2025-06-08 | 2025-06-14 | 7
| Integration and Testing | Tejaswini Kolapkar and Janhavi Pawar | 35% | 2025-06-13 | 2025-06-15 | 3
Testing, Deployment and Review
| Testing & Bug Fixing | Janhavi Pawar |  | 2025-06-15 | 2025-06-17 | 3
| Final Deployment | Tanvi Tonge |  | 2025-06-17 | 2025-06-18 | 2
| Final demo and Presentation | Tejaswini Kolapkar |  | 2025-06-18 | 2025-06-19 | 2
| Project Documentation | Shravani Pidurkar |  | 2025-06-19 | 2025-06-20 | 2
Insert new rows ABOVE this one