## Project Schedule
|  |  |  | Project start: | [7 empty] | 2025-05-28
|  |  |  | Display week: | [7 empty] | 1
|  |  |  | 2025-05-26 | [6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14
| TASK | START | END | time axis 2025-05-26 to 2025-07-20
 | time axis 2025-05-26 to 2025-07-20
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Ideation
| Define Problem Statement | 2025-05-28 | 2025-05-29
| UI Wireframing | 2025-05-29 | 2025-06-02
| ERD chart and Mind Maps | 2025-05-29 | 2025-06-02
| Gantt Chart | 2025-05-29 | 2025-06-02
| RACI Chart | 2025-05-29 | 2025-06-02
| Project Charter | 2025-05-29 | 2025-06-02
Design and Prototyping
| Create detailed wireframe | 2025-06-02 | 2025-06-04
| Finalize databara ERD | 2025-06-02 | 2025-06-04
| Finalize UI/UX designer | 2025-06-02 | 2025-06-04
| Create APl-endpoint plan | 2025-06-02 | 2025-06-05
Implementation
| Database Creation & Management | 2025-06-06 | 2025-06-12
| Frontend Development | 2025-06-08 | 2025-06-14
| Backend API development | 2025-06-08 | 2025-06-14
| Integration and Testing | 2025-06-13 | 2025-06-15
Testing, Deployment and Review
| Testing & Bug Fixing | 2025-06-15 | 2025-06-17
| Final Deployment | 2025-06-17 | 2025-06-18
| Final demo and Presentation | 2025-06-18 | 2025-06-19
| Project Documentation | 2025-06-19 | 2025-06-20

## Project actual
[6 empty] | Project Start Date | [7 empty] | 2025-05-28
[6 empty] | Current Week | [7 empty] | 2
[6 empty] | 2025-06-02 | [6 empty] | 2025-06-09 | [6 empty] | 2025-06-16 | [6 empty] | 2025-06-23 | [6 empty] | 2025-06-30 | [6 empty] | 2025-07-07 | [6 empty] | 2025-07-14 | [6 empty] | 2025-07-21
| TASK | PROGRESS | START | END | time axis 2025-06-02 to 2025-07-27
 | time axis 2025-06-02 to 2025-07-27
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning and Ideation
| Define Problem Statement | 100% | 2025-05-28 | 2025-05-29 | 2
| UI Wireframing | 100% | 2025-05-29 | 2025-06-02 | 5
| ERD chart and Mind Maps | 100% | 2025-05-29 | 2025-06-02 | 5
| Gantt Chart | 100% | 2025-05-29 | 2025-06-02 | 5
| RACI Chart | 100% | 2025-05-29 | 2025-06-02
| Project Charter | 100% | 2025-05-29 | 2025-06-02 | 5
Design and Prototyping
| Create detailed wireframe | 100% | 2025-06-02 | 2025-06-04 | 3
| Finalize databara ERD | 100% | 2025-06-02 | 2025-06-04 | 3
| Finalize UI/UX designer | 100% | 2025-06-02 | 2025-06-04 | 3
| Create APl-endpoint plan | 100% | 2025-06-02 | 2025-06-06 | 5
Implementation
| Database Creation & Management | 100% | 2025-06-06 | 2025-06-12 | 7
| Frontend Development | 100% | 2025-06-08 | 2025-06-18
| Backend API development | 100% | 2025-06-08 | 2025-06-18 | 11
| Integration and Testing | 100% | 2025-06-13 | 2025-06-16 | 4
Testing, Deployment and Review
| Testing & Bug Fixing | 100% | 2025-06-16 | 2025-06-23 | 8
| Final Deployment | 100% | 2025-06-25 | 2025-07-03 | 9
| Final demo and Presentation | 100% | 2025-07-22 | 2025-07-23 | 2
| Project Documentation | 100% | 2025-07-23 | 2025-08-01 | 10
Insert new rows ABOVE this one